## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog Crime Management System Project ID: ADMAJ014/POD 3 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
1 | Homepage
Task_1 | UX page | 3 | Arpita, Suvidya | Completed | 20 | 2 | 4 | 3 | 5 | 2
Task_2 | User registration page design | 3 | Avanija | Completed | 6 | 1 | 1 | 2 | 2 | 0
Task_3 | User login page design | 3 | Vignesh K | Completed | 6 | 0 | 1 | 1 | 2 | 2
Task_4 | Creating a database | 1 | Vivek | Completed | 2 | 0 | 1 | 1 | 0 | 0
2 | User Validation
Task_1 | Create table to store registration details and connectivity | 2 | Vivek | Completed | 8 | 1 | 1 | 2 | 1 | 2
Task_2 | Generating OTP | 5 | Vignesh, Avanija | Completed | 8 | 0 | 1 | 3 | 3
Task_3 | Java code to send mail once the user has registered | 3 | Suvidya | Completed | 8 | 0 | 1 | 1 | 3 | 3
Task_4 | Testing | 2 | Arpita | Completed | 8 | 0 | 0.5 | 1 | 2 | 4.5
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 66 | 4 | 10.5 | 14 | 18 | 13.5

## Sprint -2
Sprint Backlog Crime Management System Project ID: ADMAJ014/POD 3 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
3 | User Complaint Page
Task_1 | Design user interface | 2 | Avanija | Completed | 3 | 0.5 | 0 | 1 | 1 | 0
Task_2 | Creating table to store complaints | 2 | Vivek | Completed | 8 | 1 | 2 | 4 | 0.5 | 0.5
Task_3 | Generating captcha and verifying | 5 | Suvidya | Completed | 6 | 1 | 1 | 1 | 1.5 | 1.5
Task_4 | Generating complaint Id and sending mail to the user upon receiving the complaint | 5 | Arpita | Completed | 8 | 1 | 2 | 1 | 3 | 2
4 | Police and User Login Page
Task_1 | Design | 2 | Avanija | Completed | 6 | 2 | 2 | 3 | 0 | 0
Task_2 | Devoping a code to validate the police login credentials | 3 | Arpita | Completed | 8 | 2 | 3 | 2 | 2 | 0
Task_3 | Creating police and login table | 2 | Vivek | Completed | 8 | 2 | 3 | 3 | 2 | 0
Task_4 | Devoping a code to validate the user login credentials and OTP generation | 2 | Vignesh, Suvidya | Completed | 8 | 2 | 1 | 3 | 4 | 0
User Story #3 | Sprint 1 Improvements
Task_1 | Added Timestamp for registration page | 2 | Vivek | Completed | 1 | 0 | 0.5 | 0 | 0 | 0
Task_2 | Added encryption method to password | 2 | Vivek | Completed | 1 | 0 | 0.5 | 0 | 0 | 0
Task_3 | Improved the content of the mail sent to the user | 1 | Arpita | Completed | 1 | 2 | 0 | 0 | 0 | 0
Task_4 | Create a login table to store count and last login time | 2 | Vignesh | Completed | 2 | 1 | 0 | 0 | 1 | 0
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 60 | 14.5 | 15 | 18 | 15 | 4

## Sprint -3
Sprint Backlog Crime Management System Project ID: ADMAJ014/POD 3 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
3 | Police Overview Page
Task_1 | Design complaint status page | 3 | Vignesh | Completed | 3 | 0 | 1 | 1 | 1 | 0
Task_2 | Retrieve complaints from the database, update status of the complaints in database | 3 | Avanija | Completed | 8 | 2 | 3 | 1 | 1 | 1
Task_3 | Desiging UI for police overview page | 3 | Suvidya | Completed | 8 | 1 | 1 | 3 | 3 | 1
Task_4
4 | Complaint Tracking
Task_1 | Design complaint tracking page | 3 | Arpita | Completed | 3 | 0 | 0 | 2 | 0 | 1
Task_2 | Retrieve status of the complaints from the database | 3 | Vivek | Completed | 5 | 2 | 1 | 0 | 0 | 3
Task_3
Task_4
User Story #3 | Sprint 3 Improvements
Task_1 | Block future dated in calendar | 2 | Avanija | Completed | 1 | 1 | 0 | 0 | 0 | 0
Task_2 | Pre-populate mobile number in complaint form | 1 | Arpita | Completed | 2 | 0 | 0 | 3 | 0 | 0
Task_3 | Error Messages for negative cases | 3 | Vivek | Completed | 4 | 2 | 1 | 1 | 0 | 1
Task_4 | Complaint status table | 3 | Vignesh | Completed | 3 | 0 | 0 | 1 | 2
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 37 | 8 | 7 | 12 | 7 | 7

## Sprint -4
Sprint Backlog Crime Management System Project ID: ADMAJ014/POD 3 C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
5 | Complaint Validation and User Verification
Task_1 | Designing user verification page | 3 | Arpita | Completed | 4 | 1 | 0 | 2 | 1 | 0
Task_2 | Designing complaint verification page | 3 | Vignesh | Completed | 3 | 0 | 0 | 1 | 2 | 0
Task_3 | Create admin table | 2 | Vivek | Completed | 4 | 0 | 1 | 2 | 0 | 1
Task_4 | Designing Admin overview page | 3 | Arpita | Completed | 6 | 1 | 2 | 2 | 2 | 0
6 | Police Information Update
Task_1 | Designing police update page | 3 | Suvidya, Avanija | Completed | 6 | 0 | 2 | 3 | 0 | 1
Task_2
Task_3
Task_4
User Story #3
Task_1
Task_2
Task_3
Task_4
User Story #4
Task_1
Task_2
Task_3
Task_4
User Story #5
Task_1
Task_2
Task_3
Task_4
TOTAL |  |  |  |  | 23 | 2 | 5 | 10 | 5 | 2

## Data (hidden)
In-Progress
Completed
N/A